## Sprints
Sprint | Week | Sprint Goal | Start Date | End Date | Sprint State
1 | 2/3 | Planning of Project Creation | 2024-04-08 | 2024-04-19 | Closed
2 | 4/5 | Researching Dashboard Creation Methods | 2024-04-22 | 2024-05-03 | Closed
3 | 6/7 | Creating required and NF requirements | 2024-05-06 | 2024-05-17 | Closed
MST + Term Break
4 | 12/13 | Creating Functions based on Requirement and NFR | 2024-07-02 | 2024-07-13 | Closed
5 | 14/15 | QOL Improvements | 2024-07-16 | 2024-07-27 | Active
6 | 16/17 | Bug Fix | 2024-07-30 | 2024-08-10 | Active
*NFR = Non-Functional Requirement
Formulas:
End Date = [Start Date]+11
Start Date = [Start Date, row above]+14

## Active Sprint Board (hidden)
To Do | Doing | Done

## Product Backlog
ID | Story Title | Story Description | Definition of Done | Estimated Effort (hours) | Actual Effort (hours) | Status | Sprint
1 | Planning of Project Creation | As a Software Developer, I need to think of a project that can solve the issues in this world. | A suitable problem statement that can be achieved using the Raspberry Pi board and is able to solve the issues the world is facing. | 1 | 0.5 | Done | Sprint 1
2 | Researching Dashboard Creation Methods | As a Software Developer, I need to be able to display our data in a convenient and concise manner, so that the user can analyse it clearer | A suitable dashoard that can clearly display all our values and data. | 4 | 3 | Done | Sprint 2
3 | Create Use Case Diagrams in SRS document | As a Software Developer, I need to define all the different Use Case Diagrams for the Automated Gardening System | All necessary Use Case Diagrams are defined in the SRS document SRS document is commited and pushed to Github | 10 | 5 | Done | Sprint 3
4 | Creating function for the Use Cases in the SRS document | As a Software Developer, I need to create respective functions to fulfill the requirements of the Automated Gardening System | Function are based on the requirements of Use Cases in the SRS document Functions is commited and pushed to Github | 40 | 40 | Done | Sprint 4
5 | Improvements on QOL | As a Software Developer, I need to ensure that the users of the product have a convinient way of checking the values and operates the system smoothly | Dashboard successfully displays all output values from the raspberrypi and interface runs smoothly with respective functions | 50 | 30 | Done | Sprint 5
6 | Fixing of bugs | As a Software Developer, I need to debug with pytests and check on RaspberryPi to ensure the product has no problems | Final demo working successfully without any bug issues | 50 | 150 | Done | Sprint 6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95 | [5 empty] | Doing
96
97
98
99
100

## enum (hidden)
Sprint | Start Date | End Date | Story Status | Spint State
Sprint 1 |  |  | To Do | Inactive
Sprint 2 |  |  | Doing | Active
Sprint 3 |  |  | Done | Closed
Sprint 4
Sprint 5
Sprint 6